## Slide 1: SPRINT RETROSPECTIVE Team R02
SE2 – Workshop #6

## Slide 2: PROCESS MEASURES Macro statistics
Committed Stories: 11 → Done: 0 (no unit testing performed)
Committed Points: 27 → Done: 0 (no unit testing performed)
Planned Hours: 50.5 → Spent Hours: 41.41
Story 7 -> has no tasks assigned
Task 20 assigned to story 0 or not?

## Slide 3: PROCESS MEASURES detailed statistics - 1
Story #0: Technical tasks (6 tasks)
Estimated: 15h30min → Actual: 14h10min
Story #1: (Administrator) Configuring the system with the services that each desk offers
Task #1:
Story points: 2
Estimated: 3h30min → Actual: 5h15min
Story #2: (Administrator) Configuring the service time
Task #1: Adding the configuration of service time for each desk
Story points: 1
Estimated: 3h → Actual: 2h45min

## Slide 4: PROCESS MEASURES detailed statistics - 2
Story #3: (Administrator) The system must have a queue for each service type
Task #1: Create queue system
Story points: 3
Estimated: 5h → Actual: 3h30min
Story #4: (User) Seeing all the offered service types and choosing the needed one
Task #1: Create a ticket system
Task #2: Create the UI for selecting services
Story points: 3
Estimated: 4h30min → Actual: 3h30min

## Slide 5: PROCESS MEASURES detailed statistics - 3
Story #5: (User) Receiving a ticket that has an approximate waiting time
Task #1: Calculate approximate waiting time for the ticket
Story points: 3
Estimated: 3h → Actual: 2h30min
Story #6: (Officer) Calling the next user in queue that is requesting a service that i can offer
Task #1: Calculate the next ticket to be served
Story points: 2
Estimated: 1h30min → Actual: 2h30min

## Slide 6: PROCESS MEASURES detailed statistics - 3
Story #7: Not committed
Story #8: (User) Receiving a ticket that has a unique number
Task #1: Make ticket numbers unique
Story points: 1
Estimated: 1h → Actual: 45m
Story #9: (User) Notification when the waiting time changes
Task #1: Create a notification system
Task #2: Updating the notification system
Story points: 5
Estimated: 3h30min → Actual: 2h30min

## Slide 7: PROCESS MEASURES detailed statistics - 3
Story #10: (Officer) The called user must be removed from the queue
Task #1: Removing served user
Story points: 2
Estimated: 1h30min → Actual: 3h30min
Story #11: (Administrator) Option to reset the queues every morning
Task #1: (Not committed) Compact data and move them to statistics
Task #2: Reset the queues
Story points: 3
Estimated: 5h30min → Actual: 1h15min

## Slide 8: QUALITY MEASURES UNIT TESTING
Total hours estimated: 0h (6h of studying unit testing methods)
Total hours spent: 0h (3h of studying unit testing methods)
Nr of automated unit test cases: 0
Coverage: 0%

## Slide 9: QUALITY MEASURES E2e testing
Total hours estimated: 9h30min
Total hours spent: 8h45min

## Slide 10: QUALITY MEASURES Technical debt management
Total hours estimated: 1h30min
Total hours spent: 1h30min
Hours estimated for remediation by SonarQube
Hours estimated for remediation by SonarQube only for the selected and planned issues
Hours spent on remediation
debt ratio (as reported by SonarQube under "Measures-Maintainability")
rating for each quality characteristic reported in SonarQube under "Measures" (namely reliability, security, maintainability)

## Slide 11: Assessment
What caused your errors in estimation (if any)?
Underestimated need for coordination between team members (many modules of the app were linked and were dependent on one another)
Underestimated code documentation and testing time

## Slide 12: Assessment
What lessons did you learn (both positive and negative) in this sprint?
The need for a well-documented code is essential in a team-working environment
We need to schedule more time for organization and coordination meetings
We need to better divide the tasks among team members to reduce wasted time on coordination

## Slide 13: Assessment
Which improvement goals set in the previous retrospective were you able to achieve?
Nothing

## Slide 14: Assessment
Which ones you were not able to achieve? Why?
Nothing

## Slide 15: Assessment
Improvement goals for the next sprint and how to achieve them (technical tasks, team coordination, etc.)
Loose less time in coordination efforts by estimating more hours for communication and documentation
Better define tasks to reduce task dependencies and improve the possibility for all team members to work in parallel

## Slide 16: Assessment
Things we are proud as a team:
Everyone worked really hard to provide a perfectly working demo
The communication between team members was extremely friendly